## Sheet1
| Date Completed | THINGS NEEDED
Corwin | 2009-03-09 | bytes used in gamevars
Tom | 2009-03-20 | profile manager
Dave | 2009-03-11 | updated tempart that does not look like a pile of dogshit
Corwin | 2009-03-09 | slash switched/changed in bytes used line
Corwin | 2009-03-11 | command insertion
Dave | 2009-03-09 | move forward until unable should only count as 1 command processed and not 1 for each square processed
Dave | 2009-03-09 | ice squares should only count as 1 command
Dave | 2009-03-11 | view score state should show the level and level title/description of what you just beat
C/D | 2009-03-09 | tab artwork was added as well as implemented
Dave | 2009-03-09 | level should be easier to see ingame
Tom | 2009-03-11 | in-game pause menu with load/save/quit/return to main menu/save and quit/return to game
Dave | 2009-03-11 | Level select to show picture of map as well as descriptions of map
Dave | 2009-03-11 | bytes used during game needs a black semi-transparent backdrop
Dave | 2009-03-11 | bytes used by command in tooltip
Dave | 2009-03-11 | Menus need to at the very least use better temp art
Dave | 2009-03-11 | activate needs more descriptive tooltips
Dave | 2009-03-11 | Credits needs to be implemented
Dave | 2009-03-16 | you died state has some funkiness with abort/execute
Tom | 2009-03-29 | load game needs to go to the select profile state
dave | 2009-03-29 | Condense the filesize of the content folder
Dave | 2009-03-16 | pause menu esc should fire a return to game
Dave | 2009-03-16 | compass click handlers aren't working and I have no idea why - fixed
Dave | 2009-03-16 | because level select can pop up during ingame, it needs a white background
Dave | 2009-03-17 | add mouse controlled interface for panning/zooming to elmininate keyboard input
Corwin | 2009-03-29 | corwin needs to clean up his memory
Corwin | 2009-03-30 | click to add for instructions if the block hasn't been moved
Dave | 2009-03-29 | Brief pause upon level completion, do a victory dance or whatever
Dave | 2009-03-29 | in the hover tooltips for instructions it should say what the instruction is
Dave | 2009-03-29 | punch should not automatically move you into the square
Level Designers |  | maps need balancing
help screen
Tom |  | level select/profile should have exit
Tom |  | at end of level, buttons should be, in order, advance, return to main menu
add a button to replay level when you finish a level
NIFTY SHIT TO ADD
Dave | 2009-03-29 | graphic overhaul
Dave | 2009-03-30 | rotate map left/right
"did you know" info for pregame screen
Corwin |  | menu slide in and out
teleporters and switches should not hijack the graphics engine
teleporters and switches should pan around rather than jumping
Corwin |  | component system
pause/continue - pause processing and continue processing without clearing anything
Level Editor
online support for high scores
best time
shortest algorithm
best combination
Corwin |  | if piece in hand cannot be dropped due to byte limits, piece greys out
Corwin |  | if piece in hand cannot be dropped, place command here greys out
Tom |  | we need to cleanup/comment the hell out of a lot of the code
BUGS
Dave | 2009-03-16 | on certain maps, keyboard control for panning does not work until after the mouse pans that direction first
Dave | 2009-03-09 | fix ice in subroutines
Tom | 2009-03-10 | start new game does not check for an existing file properly
Dave | 2009-03-15 | make it so you cannot resize the screen
Tom | 2009-03-29 | game saves the level you're on and not the highest level you can select
Dave | 2009-03-15 | Color of start and end squares need to stand out more
Dave | 2009-03-15 | "You died" text needs to be fixed
Dave | 2009-03-15 | Tutorial level 5, the hole can't be clearly seen because of the raised block
Dave | 2009-03-15 | devlogofades broke again, fixed now
Dave | 2009-03-30 | map centering issues verifymappositions() is where the errors are, this needs some work
subs calling subs may not be working right still, not 100% sure - last command of 2nd sub called may process an extra time
subs shouldn't be able to call themselves
if sub1/2 isn't available it shouldn't allow clicking or even draw the tabs
level ideas
ability to disable/enable/move end square
bonus stages - short out levels where commands get randomized and other fun stuff
everything you know is wrong
ability to totally disable a tile so it doesn't show up at all
for any fucked up shit we have that can work on a level, have it as a tickbox to enable it for the entire level
Feedback from testers
Dave | 2009-03-30 | Tutorial 1 needs to be inverted, with the robot going forward instead of down, as this is the first time we're seeing a map/robot
Dave | 2009-03-30 | More descriptive explanations on the hover tips
Dave | 2009-03-30 | The move forward until unable needs to be more distinguishable, maybe a larger line above a smaller arrow
Not enough continuity from action buttons (punch, climb, crouch) as in the user doesn’t always know where they will end up x2
add more descriptive tooltips
The hole tile isn't clear that it’s a hole in the floor.
Raised tiles need to be shorter to improve visibility of the map - different color tile tops, as well as better designed levels
Jump needs a new icon
Turn off all debug shit