## Sheet1
| Date Completed | THINGS NEEDED
Corwin | 2009-03-09 | bytes used in gamevars
profile manager
Dave | 2009-03-11 | updated tempart that does not look like a pile of dogshit
Corwin | 2009-03-09 | slash switched/changed in bytes used line
Corwin | 2009-03-11 | command insertion
Dave | 2009-03-09 | move forward until unable should only count as 1 command processed and not 1 for each square processed
Dave | 2009-03-09 | ice squares should only count as 1 command
Dave | 2009-03-11 | view score state should show the level and level title/description of what you just beat
C/D | 2009-03-09 | tab artwork was added as well as implemented
Dave | 2009-03-09 | level should be easier to see ingame
Tom | 2009-03-11 | in-game pause menu with load/save/quit/return to main menu/save and quit/return to game
Dave | 2009-03-11 | Level select to show picture of map as well as descriptions of map
Dave | 2009-03-11 | bytes used during game needs a black semi-transparent backdrop
Dave | 2009-03-11 | bytes used by command in tooltip
Dave | 2009-03-11 | Menus need to at the very least use better temp art
Dave | 2009-03-11 | activate needs more descriptive tooltips
you died state has some funkiness with abort/execute
Level Designers |  | maps need balancing
Corwin |  | menu slide in and out
Tom |  | saving games needs to save board state if a reprogram switch was hit
corwin needs to clean up his memory
Credits needs to be implemented
NIFTY SHIT TO ADD
teleporters and switches should not hijack the graphics engine
teleporters and switches should pan around rather than jumping
Corwin |  | component system
graphic overhaul
pause/continue - pause processing and continue processing without clearing anything
Level Editor
online support for high scores
best time
shortest algorithm
best combination
if piece in hand cannot be dropped due to byte limits, piece greys out
if piece in hand cannot be dropped, place command here greys out
rotate map left/right
BUGS
on certain maps, keyboard control for panning does not work until after the mouse pans that direction first
Dave | 2009-03-09 | fix ice in subroutines
Tom | 2009-03-10 | start new game does not check for an existing file properly
make it so you cannot resize the screen
subs calling subs may not be working right still, not 100% sure
Tom |  | game saves the level you're on and not the highest level you can select
level ideas
ability to disable/enable end square
bonus stages - short out levels where commands get randomized and other fun stuff
everything you know is wrong