## Sheet1
| Date Completed | THINGS NEEDED
Corwin | 2009-03-09 | bytes used in gamevars
profile manager
Dave |  | updated tempart that does not look like a pile of dogshit
Corwin |  | menu slide in and out
Corwin |  | KGA1 - SG350
Tom |  | saving games needs to save board state if a reprogram switch was hit
Corwin |  | bytes used by command in tooltip
Corwin | 2009-03-09 | slash switched/changed in bytes used line
Corwin |  | command insertion
Dave | 2009-03-09 | move forward until unable should only count as 1 command processed and not 1 for each square processed
Dave | 2009-03-09 | ice squares should only count as 1 command
Dave |  | view score state should show the level and level title/description of what you just beat
you died state has some funkiness with abort/execute
maps need balancing
C/D | 2009-03-09 | tab artwork was added as well as implemented
corwin needs to clean up his memory
Dave | 2009-03-09 | level should be easier to see ingame
NIFTY SHIT TO ADD
teleporters and switches should not hijack the graphics engine
teleporters and switches should pan around rather than jumping
Corwin |  | component system
graphic overhaul
pause/continue - pause processing and continue processing without clearing anything
Level Editor
Level select to show picture of map as well as descriptions of map
online support for high scores
best time
shortest algorithm
best combination
if piece in hand cannot be dropped due to byte limits, piece greys out
if piece in hand cannot be dropped, place command here greys out
rotate map left/right
| [ | BUGS
on certain maps, keyboard control for panning does not work until after the mouse pans that direction first
Dave | 2009-03-09 | fix ice in subroutines
start new game does not check for an existing file properly