## Sheet1
| Date Completed | THINGS NEEDED
Corwin | 2009-03-09 | bytes used in gamevars
Tom | 2009-03-20 | profile manager
Dave | 2009-03-11 | updated tempart that does not look like a pile of dogshit
Corwin | 2009-03-09 | slash switched/changed in bytes used line
Corwin | 2009-03-11 | command insertion
Dave | 2009-03-09 | move forward until unable should only count as 1 command processed and not 1 for each square processed
Dave | 2009-03-09 | ice squares should only count as 1 command
Dave | 2009-03-11 | view score state should show the level and level title/description of what you just beat
C/D | 2009-03-09 | tab artwork was added as well as implemented
Dave | 2009-03-09 | level should be easier to see ingame
Tom | 2009-03-11 | in-game pause menu with load/save/quit/return to main menu/save and quit/return to game
Dave | 2009-03-11 | Level select to show picture of map as well as descriptions of map
Dave | 2009-03-11 | bytes used during game needs a black semi-transparent backdrop
Dave | 2009-03-11 | bytes used by command in tooltip
Dave | 2009-03-11 | Menus need to at the very least use better temp art
Dave | 2009-03-11 | activate needs more descriptive tooltips
Dave | 2009-03-11 | Credits needs to be implemented
Dave | 2009-03-16 | you died state has some funkiness with abort/execute
Tom | 2009-03-29 | load game needs to go to the select profile state
dave | 2009-03-29 | Condense the filesize of the content folder
Dave | 2009-03-16 | pause menu esc should fire a return to game
Dave | 2009-03-16 | compass click handlers aren't working and I have no idea why - fixed
Dave | 2009-03-16 | because level select can pop up during ingame, it needs a white background
Dave | 2009-03-17 | add mouse controlled interface for panning/zooming to elmininate keyboard input
Corwin | 2009-03-29 | corwin needs to clean up his memory
Corwin | 2009-03-30 | click to add for instructions if the block hasn't been moved
Dave | 2009-03-29 | Brief pause upon level completion, do a victory dance or whatever
Dave | 2009-03-29 | in the hover tooltips for instructions it should say what the instruction is
Dave | 2009-03-29 | punch should not automatically move you into the square
Level Designers | 2009-04-04 | maps need balancing
Dave | 2009-04-01 | help screen
Tom | 2009-03-30 | level select/profile should have exit
Tom | 2009-03-30 | at end of level, buttons should be, in order, advance, return to main menu
Tom | 2009-03-30 | add a button to replay level when you finish a level
Tom | 2009-04-02 | When in mid game, if you leave to main menu and create a new profile, it wipes out the save file / all saving files aren't working properly
Tom | 2009-04-01 | Level select from create profile doesn’t erase its state
Dave | 2009-04-04 | Select profile state needs a "back" button
Dave | 2009-04-04 | Under create new game, if profile already exists, there needs to be a back button
Dave | 2009-04-04 | select level should show what your highest level available is
Dave | 2009-04-04 | level select should show the score for the current level
Dave | 2009-04-05 | in game should show the level number
when activating a reprogram square, the "abort" button needs to trigger into an execute button…
when you hit save game in pause menu, it needs to fire a click ok state
nuke save game button from options menu
update all map mini images to match the current maps, AFTER all the maps have been cleaned up/tweaked
NIFTY SHIT TO ADD
Dave | 2009-03-29 | graphic overhaul
Dave | 2009-03-30 | rotate map left/right
Corwin | 2009-04-01 | if piece in hand cannot be dropped due to byte limits, piece greys out
Corwin | 2009-04-01 | if piece in hand cannot be dropped, place command here greys out
Dave | 2009-04-03 | "did you know" info for pregame screen
Dave | 2009-04-05 | Scoring changes - almost no bonus on tutorials, tons more on regular levels
Corwin |  | menu slide in and out
Dave | 2009-04-05 | switches should not hijack the graphics engine
teleporters should not hijack the graphics engine
teleporters and switches should pan around rather than jumping
Corwin |  | component system
pause/continue - pause processing and continue processing without clearing anything
Level Editor
online support for high scores
best time
shortest algorithm
best combination
Tom |  | we need to cleanup/comment the hell out of a lot of the code
for 1.1.. offline high scores?
BUGS
Dave | 2009-03-16 | on certain maps, keyboard control for panning does not work until after the mouse pans that direction first
Dave | 2009-03-09 | fix ice in subroutines
Tom | 2009-03-10 | start new game does not check for an existing file properly
Dave | 2009-03-15 | make it so you cannot resize the screen
Tom | 2009-03-29 | game saves the level you're on and not the highest level you can select
Dave | 2009-03-15 | Color of start and end squares need to stand out more
Dave | 2009-03-15 | "You died" text needs to be fixed
Dave | 2009-03-15 | Tutorial level 5, the hole can't be clearly seen because of the raised block
Dave | 2009-03-15 | devlogofades broke again, fixed now
Dave | 2009-03-30 | map centering issues verifymappositions() is where the errors are, this needs some work
IRRELEVANT - subs can't call subs anymoresubs calling subs may not be working right still, not 100% sure - last command of 2nd sub called may process an extra time
Corwin | 2009-04-02 | subs shouldn't be able to call themselves |  |  | Note: Subs redesigned to not call any other subs
Corwin | 2009-03-30 | if sub1/2 isn't available it shouldn't allow clicking or even draw the tabs
Dave | 2009-03-30 | move forward until unable does not end its trigger when facing a door
Dave | 2009-04-04 | if you put in a lot of commands with auto click and it adds another row, it should auto-scroll to next row
if you put in a lot of commands, while processing it should auto-scroll to the next row
Dave | 2009-04-04 | if you drag an instruction into the instruction list, it drops it as if it was on the first page and not on the current scroll page
replay level needs a total restart of map, it is picking up from the repgoram square
if you put in a lot of commands, while processing you should be able to scroll the instruction list
this looks as if it should be functioning… not sure why it isn't
Dave | 2009-04-04 | switches and teleporters aren't rotating with the map (they are visually, not in the object list)
when sub1/sub2 are selected and they are propmtly greyed out, it kindly informs you that there is not enough memory to use this
current processed command is not showing the sub as being processed, but instead the previous command being processed
if inside a sub, it should highlight that sub in the main command list
level ideas
ability to disable/enable/move end square
bonus stages - short out levels where commands get randomized and other fun stuff
everything you know is wrong
ability to totally disable a tile so it doesn't show up at all
for any fucked up shit we have that can work on a level, have it as a tickbox to enable it for the entire level
Feedback from testers
Dave | 2009-03-30 | Tutorial 1 needs to be inverted, with the robot going forward instead of down, as this is the first time we're seeing a map/robot
Dave | 2009-03-30 | More descriptive explanations on the hover tips
Dave | 2009-03-30 | The move forward until unable needs to be more distinguishable, maybe a larger line above a smaller arrow
Dave | 2009-03-30 | The hole tile isn't clear that it’s a hole in the floor.
Not enough continuity from action buttons (punch, climb, crouch) as in the user doesn’t always know where they will end up x2
add more descriptive tooltips
Raised tiles need to be shorter to improve visibility of the map - different color tile tops, as well as better designed levels
Jump needs a new icon
Turn off all debug shit
|  | normal | subs | reprogram
c1 | 1 | 56 |  |  | short and sweet
g1 | 6 | 78 |  |  | very easy, should be an earlier level
g2 | 7 | 64 |  |  | very easy, should be an earlier level
c3 | 3 | 110 |  | 62 with reprogram | not too bad
o1 | 11 | 128 |  |  | not very complex, fairly easy as well - lots of random extra stuff not related to finishing the map
g5 | 10 | 154 |  |  | easy - very straightforward
g3 | 8 | 156 |  |  | fairly easy - fun water map | jump-move forward and jump-move forward 3 are EASILY mass repeated on this map, will test with subs | sub1 = jump/move forward, sub2 = jump
o3 | 13 | 182 |  |  | could probably lose the reprogram square, additionally, not sure if intended, but the last two switches can be skipped entirely, may want to disable jump on this map, or make some reason for the switches
g4 | 9 | 306 | 164 |  | fun - lots of jumping
o4 | 14 | 318 |  |  | very linear, interesting figuring out what does what
o2 | 12 |  |  |  | can't be beaten
o5 | 15 |  |  |  | can't be beaten
c5 | 5 | 92 |  |  | annoying as hell |  |  | fixed bad switch
c4 | 4 | 88 |  |  | annoying as hell |  |  | used left switch
c2 | 2 | 156 |  |  | annoying as hell
tutorial map 7 - remove the two solid blocks