## Sheet1
To Do List
Tom | 2009-04-10 | replay level breaks the instruction list highlighting for current level
Tom | 2009-04-10 | total score needs to be calculated on the fly based off of all your level scores
Dave | 2009-04-10 | re-design tutorial levels - need less of them
Dave | 2009-04-10 | move climbing revist to a normal level
Dave | 2009-04-10 | make an easier climbing level
Dave | 2009-04-10 | make climbing tutorial a normal level
Dave | 2009-04-10 | add to the switch art a red edge so it is clear what edge to use
Dave | 2009-04-10 | re-design switch map to make it more obvious/intuitive
Dave | 2009-04-10 | add a reprogram tutoriallevel
Dave | 2009-04-10 | up and left scrolls need to check position zero
Dave | 2009-04-10 | move teleport level to a later level
Dave | 2009-04-10 | add new teleport tutorial
Dave | 2009-04-10 | add new climb level
Corwin | 2009-04-10 | make buttons so holding down click continuously fires the effect
Corwin | 2009-04-10 | certain circumstances allow you to insert too many commands after a reprogram has been hit
Corwin | 2009-04-10 | make select profile showing level description use new font splitter
Corwin | 2009-04-10 | make black block behind level info ingame go across the screen
Corwin | 2009-04-10 | add drawtext function support including the new parsing feature whee
Dave | 2009-04-10 | circle in compass needs to reset zoom as well when it centers on robot
Corwin | 2009-04-10 | make pregame text use new font splitter and be smaller text
Dave | 2009-04-10 | Bind < > to speed up and slow down
Corwin | 2009-04-10 | double check all text blocks, i.e. the text for click ok state inside of reprogram click up
Dave | 2009-04-10 | switch crouching/climbing/jumping - make it a dropoff
Corwin | 2009-04-10 | ingame - top of screen info - move level name up to same line as level number
Dave | 2009-04-10 | update new map pngs
Corwin | 2009-04-10 | destructor for font splitter
Dave | 2009-04-10 | maybe - change help interface png
Tom | 2009-04-11 | BUG - Tom sucks - deletion of last profile spawned auto-delete of the rest of the profiles
Dave | 2009-04-16 | BUG - if you click abort during victory dance, you get stuck
if you execute then abort, then try to insert just after the lit item, crash
DO NOT TOUCH THESE UNTIL ALL YOUR KGA'S ARE DONE, DOESN'T MATTER WHICH CLASS, DO THEM FIRST
Dave | 2009-04-16 | do you want to play the tutorials popup on new profile creation
high scores
tutorials - add a button for skipping level
if there is no save file and you fire up the game, and create a new profile and enter game it crashes
| Date Completed | THINGS NEEDED
Corwin | 2009-03-09 | bytes used in gamevars
Corwin | 2009-03-09 | slash switched/changed in bytes used line
Dave | 2009-03-09 | move forward until unable should only count as 1 command processed and not 1 for each square processed
Dave | 2009-03-09 | ice squares should only count as 1 command
C/D | 2009-03-09 | tab artwork was added as well as implemented
Dave | 2009-03-09 | level should be easier to see ingame
Dave | 2009-03-11 | updated tempart that does not look like a pile of dogshit
Corwin | 2009-03-11 | command insertion
Dave | 2009-03-11 | view score state should show the level and level title/description of what you just beat
Tom | 2009-03-11 | in-game pause menu with load/save/quit/return to main menu/save and quit/return to game
Dave | 2009-03-11 | Level select to show picture of map as well as descriptions of map
Dave | 2009-03-11 | bytes used during game needs a black semi-transparent backdrop
Dave | 2009-03-11 | bytes used by command in tooltip
Dave | 2009-03-11 | Menus need to at the very least use better temp art
Dave | 2009-03-11 | activate needs more descriptive tooltips
Dave | 2009-03-11 | Credits needs to be implemented
Dave | 2009-03-16 | you died state has some funkiness with abort/execute
Dave | 2009-03-16 | pause menu esc should fire a return to game
Dave | 2009-03-16 | compass click handlers aren't working and I have no idea why - fixed
Dave | 2009-03-16 | because level select can pop up during ingame, it needs a white background
Dave | 2009-03-17 | add mouse controlled interface for panning/zooming to elmininate keyboard input
Tom | 2009-03-20 | profile manager
Tom | 2009-03-29 | load game needs to go to the select profile state
dave | 2009-03-29 | Condense the filesize of the content folder
Corwin | 2009-03-29 | corwin needs to clean up his memory
Dave | 2009-03-29 | Brief pause upon level completion, do a victory dance or whatever
Dave | 2009-03-29 | in the hover tooltips for instructions it should say what the instruction is
Dave | 2009-03-29 | punch should not automatically move you into the square
Corwin | 2009-03-30 | click to add for instructions if the block hasn't been moved
Tom | 2009-03-30 | level select/profile should have exit
Tom | 2009-03-30 | at end of level, buttons should be, in order, advance, return to main menu
Tom | 2009-03-30 | add a button to replay level when you finish a level
Dave | 2009-04-01 | help screen
Tom | 2009-04-01 | Level select from create profile doesn’t erase its state
Tom | 2009-04-02 | When in mid game, if you leave to main menu and create a new profile, it wipes out the save file / all saving files aren't working properly
Level Designers | 2009-04-04 | maps need balancing
Dave | 2009-04-04 | Select profile state needs a "back" button
Dave | 2009-04-04 | Under create new game, if profile already exists, there needs to be a back button
Dave | 2009-04-04 | select level should show what your highest level available is
Dave | 2009-04-04 | level select should show the score for the current level
Dave | 2009-04-05 | in game should show the level number
Dave | 2009-04-05 | when you hit save game in pause menu, it needs to fire a click ok state
Tom | 2009-04-05 | make reset button, reset zoom as well
Tom | 2009-04-05 | processor speed to speed up/slow down processing yay
Tom | 2009-04-05 | help screen needs to load on create new profile
Tom | 2009-04-05 | flip the location of reset and clear buttons
Tom | 2009-04-05 | go ahead, delete your save game, then go click load profile, then go try making a new profile, try it I dare you
Corwin | 2009-04-07 | when activating a reprogram square, the "abort" button needs to trigger into an execute button…
Tom | 2009-04-07 | when robot hits a reprogram square, it should do a popup
Dave | 2009-04-07 | update all map mini images to match the current maps, AFTER all the maps have been cleaned up/tweaked
Dave | 2009-04-07 | switches need to toggle
Dave | 2009-04-07 | delete profile should let you cycle through profiles then click a big ass button that says delete (in dave's opinion) - tom says fuck you dave and begrudgingly agrees
Dave | 2009-04-07 | help needs to be "strategically" placed in the click ok state
Tom | 2009-04-07 | when game runs in fullscreen, it hijacks the windows resolution
update help for interface to have new positions for buttons and speed and stuff
NIFTY SHIT TO ADD
Dave | 2009-03-29 | graphic overhaul
Dave | 2009-03-30 | rotate map left/right
Corwin | 2009-04-01 | if piece in hand cannot be dropped due to byte limits, piece greys out
Corwin | 2009-04-01 | if piece in hand cannot be dropped, place command here greys out
Dave | 2009-04-03 | "did you know" info for pregame screen
Dave | 2009-04-05 | Scoring changes - almost no bonus on tutorials, tons more on regular levels
Dave | 2009-04-05 | switches should not hijack the graphics engine
Dave | 2009-04-06 | new instruction - stop command
Corwin |  | menu slide in and out
teleporters should not hijack the graphics engine
teleporters and switches should pan around rather than jumping
Corwin |  | component system
pause/continue - pause processing and continue processing without clearing anything
Dave |  | Level Editor
online support for high scores
best time
shortest algorithm
best combination
Tom |  | we need to cleanup/comment the hell out of a lot of the code
for 1.1.. offline high scores?
mouse clicks should NOT be screen pixel location dependant, but instead screen percentage location dependant
make a zoom to extents function
switch map files to use the enum names instead of ints
BUGS
Dave | 2009-03-09 | fix ice in subroutines
Tom | 2009-03-10 | start new game does not check for an existing file properly
Dave | 2009-03-15 | make it so you cannot resize the screen
Dave | 2009-03-15 | Color of start and end squares need to stand out more
Dave | 2009-03-15 | "You died" text needs to be fixed
Dave | 2009-03-15 | Tutorial level 5, the hole can't be clearly seen because of the raised block
Dave | 2009-03-15 | devlogofades broke again, fixed now
Dave | 2009-03-16 | on certain maps, keyboard control for panning does not work until after the mouse pans that direction first
Tom | 2009-03-29 | game saves the level you're on and not the highest level you can select
Dave | 2009-03-30 | map centering issues verifymappositions() is where the errors are, this needs some work
Corwin | 2009-03-30 | if sub1/2 isn't available it shouldn't allow clicking or even draw the tabs |  |  | Note: Subs redesigned to not call any other subs
Dave | 2009-03-30 | move forward until unable does not end its trigger when facing a door
Corwin | 2009-04-02 | subs shouldn't be able to call themselves
Dave | 2009-04-04 | if you put in a lot of commands with auto click and it adds another row, it should auto-scroll to next row
Dave | 2009-04-04 | if you drag an instruction into the instruction list, it drops it as if it was on the first page and not on the current scroll page
Dave | 2009-04-04 | switches and teleporters aren't rotating with the map (they are visually, not in the object list)
Tom | 2009-04-05 | replay level needs a total restart of map, it is picking up from the repgoram square
Corwin | 2009-04-06 | if you put in a lot of commands, while processing it should auto-scroll to the next row
Corwin | 2009-04-07 | if you put in a lot of commands, while processing you should be able to scroll the instruction list
Corwin | 2009-04-07 | when sub1/sub2 are selected and they are propmtly greyed out, it kindly informs you that there is not enough memory to use this
Corwin | 2009-04-07 | current processed command is not showing the sub as being processed, but instead the previous command being processed
if inside a sub, it should highlight that sub in the main command list
Corwin | 2009-04-07 | speed up/down images draw behind dragged command
Dave | 2009-04-07 | stops may not be working inside subs
IRRELEVANT - subs can't call subs anymoresubs calling subs may not be working right still, not 100% sure - last command of 2nd sub called may process an extra time
Dave/Corwin | 2009-04-09 | new font system that relies on images instead of ttfs
level ideas
ability to disable/enable/move end square
bonus stages - short out levels where commands get randomized and other fun stuff
everything you know is wrong
ability to totally disable a tile so it doesn't show up at all
for any fucked up shit we have that can work on a level, have it as a tickbox to enable it for the entire level
Feedback from testers
Dave | 2009-03-30 | Tutorial 1 needs to be inverted, with the robot going forward instead of down, as this is the first time we're seeing a map/robot
Dave | 2009-03-30 | More descriptive explanations on the hover tips
Dave | 2009-03-30 | The move forward until unable needs to be more distinguishable, maybe a larger line above a smaller arrow
Dave | 2009-03-30 | The hole tile isn't clear that it’s a hole in the floor.
Not enough continuity from action buttons (punch, climb, crouch) as in the user doesn’t always know where they will end up x2
add more descriptive tooltips
Raised tiles need to be shorter to improve visibility of the map - different color tile tops, as well as better designed levels
Jump needs a new icon
Turn off all debug shit
|  | normal | subs | memory given | reprogram
c1 | 1 | 56 |  | 64 |  | short and sweet
g1 | 6 | 78 |  | 90 |  | very easy, should be an earlier level
g2 | 7 | 64 |  | 82 |  | very easy, should be an earlier level
c3 | 3 | 110 |  | 128 | 62 with reprogram | not too bad
o1 | 11 | 128 |  | 140 |  | not very complex, fairly easy as well - lots of random extra stuff not related to finishing the map
g5 | 10 | 154 |  | 164 |  | easy - very straightforward
g3 | 8 | 156 |  | 164 |  | fairly easy - fun water map | jump-move forward and jump-move forward 3 are EASILY mass repeated on this map, will test with subs | sub1 = jump/move forward, sub2 = jump
g4 | 9 | 306 | 164 | 364 |  | fun - lots of jumping
o2 | 12 | 242 |  | 256 | 250
o3 | 13 | 296 | 438 | 512 | needs rebalance
o5 | 15 | 442 |  | 512
o4 | 14 | 792 |  | 812 |  | very linear, interesting figuring out what does what
map c2 - try with no electric walls